## Sheet1
| February |  |  |  | March |  |  |  | April
Project Week | 6 | 13 | 20 | 27 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24
Phase 1
Components
Phase 2
Schematic
PCB Board and Soldering
3D Print
Phase 3
Code and Test Runs
Code and Test Runs with Google Assistant
Action | Tasks |  |  | Finished |  |  | Starting Date |  | Ended Date |  | Budget |  | Status | Progress Bar
Components Listing | List and buy all the necessary components | [5 empty] | 06/02/2023 |  | 13/02/2023 |  | ~$30 |  | started | 20%
Schematics | Draw the PCB boards | [5 empty] | 13/02/2023 |  | 27/02/2023 |  |  |  | not started | -
PCB Board and Soldering | Have the already built board at the end of the week and start on soldering the components on top | [5 empty] | 27/02/2023 |  | 13/03/2023 |  |  |  | not started | -
3D Printing | Import the STLs to the 3D printers and finish printing all the components | [5 empty] | 13/03/2023 |  | 20/03/2023 |  |  |  | not started | -
Code and Test Runs | Test Runs the mechanics with the self control. If it's successful, proceed to adjust the code to google assistant | [5 empty] | 20/03/2023 |  | 27/03/2023 |  |  |  | not started | -
Code and Test Runs with Google Assistant | Adjust the code to add with google assistant | [5 empty] | 27/03/2023 |  | 03/04/2023 |  |  |  | not started | -